## Original
Label | Start of Term |  | 13th October Project Proposal |  | 23rd October Revised Project Proposal | [5 empty] | 8th December Interim Report | [19 empty] | 24th April Dissertation Hand In |  | TBA Demo
Week | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30
Documentation
Project Proposal | bar: 2017-10-02 to 2017-10-09
Revised Project Proposal | bar: 2017-10-16
Interrim Report | bar: 2017-11-27 to 2017-12-04
Structure Sections | bar: 2018-03-19
Dissertation | bar: 2018-03-26 to 2018-04-16
Research
Evolutionary Algorithms | bar: 2017-10-23
Review languages for EAs | bar: 2017-10-23
Representation | bar: 2017-11-06
Advanced EA methods | bar: 2018-01-22 to 2018-01-29
Memetic Algorithms
Development
Create GA Structure | bar: 2017-10-30
Representation | bar: 2017-11-06 to 2017-11-13
Data import | bar: 2017-11-13 to 2017-11-20
Validation Method | bar: 2017-11-20 to 2017-11-27
Basic Methods for GA | bar: 2017-12-11 to 2017-12-18
Bug Fixing 1 | bar: 2017-12-25 to 2018-01-08
Advanced Methods for GA | bar: 2018-01-29 to 2018-02-05
Memetic Algorithms | bar: 2018-02-12 to 2018-02-26
Bug Fixing 2 | bar: 2018-03-05 to 2018-03-12
Misc
Install software | bar: 2017-10-23 to 2017-10-30
Run Basic Methods | bar: 2018-01-01 to 2018-01-08
Other Commitments
Welcome Week | bar: 2017-09-25
Christmas Holiday | bar: 2017-12-18 to 2018-01-08
Autumn Exams | bar: 2018-01-15 to 2018-01-22
Easter Holiday | bar: 2018-03-26 to 2018-04-16

## Interim Report
Label | Start of Term |  | 13th October Project Proposal |  | 23rd October Revised Project Proposal | [5 empty] | 8th December Interim Report | [19 empty] | 24th April Dissertation Hand In |  |  | 17/18th May Presentation and Demo
Week | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21
Documentation
Project Proposal | bar: 2017-10-02 to 2017-10-09
Revised Project Proposal | bar: 2017-10-16
Interrim Report | bar: 2017-11-06 to 2017-12-04
Structure Sections | bar: 2018-03-19
Dissertation | bar: 2018-03-26 to 2018-04-16
Research
Evolutionary Algorithms | bar: 2017-10-23
Review languages for EAs | bar: 2017-10-23
Representation | bar: 2017-11-13
Poké API | bar: 2017-11-20; 2017-12-11
Advanced EA methods | bar: 2018-01-22 to 2018-01-29
Memetic Algorithms
Development
Create GA Structure | bar: 2017-10-30 to 2017-11-06
Run GA on Benchmark Function | bar: 2017-11-06 to 2017-11-13
Representation | bar: 2017-11-20; 2017-12-11
Data import | bar: 2017-12-11 to 2017-12-18
Validation Method | bar: 2017-12-25 to 2018-01-01
Basic Methods for GA | bar: 2018-01-08; 2018-01-22
Bug Fixing 1 | bar: 2017-12-25 to 2018-01-08
Advanced Methods for GA | bar: 2018-01-29 to 2018-02-05
Memetic Algorithms | bar: 2018-02-12 to 2018-02-26
Bug Fixing 2 | bar: 2018-03-05 to 2018-03-12
Demo
Work on Presentation | bar: 2018-04-30 to 2018-05-07
Finalise Presentation | bar: 2018-05-14
Misc
Install software | bar: 2017-10-23 to 2017-10-30
Run Basic Methods | bar: 2018-01-01 to 2018-01-08
Other Commitments
Welcome Week | bar: 2017-09-25
Christmas Holiday | bar: 2017-12-18 to 2018-01-08
Autumn Exams | bar: 2018-01-15 to 2018-01-22
Easter Holiday | bar: 2018-03-26 to 2018-04-16

## Dissertation
Label | Start of Term |  | 13th October Project Proposal |  | 23rd October Revised Project Proposal | [5 empty] | 8th December Interim Report | [19 empty] | 24th April Dissertation Hand In |  |  | 17/18th May Presentation and Demo
Week | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14
Documentation
Project Proposal | bar: 2017-10-02 to 2017-10-09
Revised Project Proposal | bar: 2017-10-16
Interrim Report | bar: 2017-11-06 to 2017-12-04
Structure Sections | bar: 2018-03-19
Dissertation | bar: 2018-03-26 to 2018-04-16
Research
Evolutionary Algorithms | bar: 2017-10-23
Review languages for EAs | bar: 2017-10-23
Representation | bar: 2017-11-13
Poké API | bar: 2017-11-20; 2017-12-11
Memetic Algorithms | bar: 2018-02-26
Development
Create GA Structure | bar: 2017-10-30 to 2017-11-06
Run GA on Benchmark Function | bar: 2017-11-06 to 2017-11-13
Representation | bar: 2017-11-20; 2017-12-11
Data import | bar: 2017-12-11 to 2017-12-18
Validation Method | bar: 2017-12-25 to 2018-01-01
Basic Methods for GA | bar: 2018-01-08; 2018-01-22 to 2018-02-05
Bug Fixing 1 | bar: 2017-12-25 to 2018-01-08
Memetic Algorithms | bar: 2018-03-05 to 2018-03-12
Bug Fixing 2 | bar: 2018-03-12 to 2018-03-19
Demo
Work on Presentation | bar: 2018-04-30 to 2018-05-07
Finalise Presentation | bar: 2018-05-14
Misc
Install software | bar: 2017-10-23 to 2017-10-30
Run Basic Methods | bar: 2018-01-01 to 2018-01-08
Running of Final Code | bar: 2018-03-26 to 2018-04-02
Other Commitments
Welcome Week | bar: 2017-09-25
Christmas Holiday | bar: 2017-12-18 to 2018-01-08
Autumn Exams | bar: 2018-01-15 to 2018-01-22
G53DIA Coursework | bar: 2018-02-12 to 2018-02-19; 2018-03-19 to 2018-03-26
Easter Holiday | bar: 2018-03-26 to 2018-04-16

## Dissertation to print
Label | Start of Term |  | 13th October Project Proposal |  | 23rd October Revised Project Proposal | [5 empty] | 8th December Interim Report
Week | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04
Documentation
Project Proposal | bar: 2017-10-02 to 2017-10-09
Revised Project Proposal | bar: 2017-10-16
Interrim Report | bar: 2017-11-06 to 2017-12-04
Structure Sections
Dissertation
Research
Evolutionary Algorithms | bar: 2017-10-23
Review languages for EAs | bar: 2017-10-23
Representation | bar: 2017-11-13
Poké API | bar: 2017-11-20
Memetic Algorithms
Development
Create GA Structure | bar: 2017-10-30 to 2017-11-06
Run GA on Benchmark Function | bar: 2017-11-06 to 2017-11-13
Representation | bar: 2017-11-20
Data import
Validation Method
Basic Methods for GA
Bug Fixing 1
Memetic Algorithms
Bug Fixing 2
Demo
Work on Presentation
Finalise Presentation
Misc
Install software | bar: 2017-10-23 to 2017-10-30
Run Basic Methods
Running of Final Code
Other Commitments
Welcome Week | bar: 2017-09-25
Christmas Holiday
Autumn Exams
G53DIA Coursework
Easter Holiday
Label
Week | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19
Documentation
Project Proposal
Revised Project Proposal
Interrim Report
Structure Sections
Dissertation
Research
Evolutionary Algorithms
Review languages for EAs
Representation
Poké API | bar: 2017-12-11
Memetic Algorithms
Development
Create GA Structure
Run GA on Benchmark Function
Representation | bar: 2017-12-11
Data import | bar: 2017-12-11 to 2017-12-18
Validation Method | bar: 2017-12-25 to 2018-01-01
Basic Methods for GA | bar: 2018-01-08; 2018-01-22 to 2018-02-05
Bug Fixing 1 | bar: 2017-12-25 to 2018-01-08
Memetic Algorithms
Bug Fixing 2
Demo
Work on Presentation
Finalise Presentation
Misc
Install software
Run Basic Methods | bar: 2018-01-01 to 2018-01-08
Running of Final Code
Other Commitments
Welcome Week
Christmas Holiday | bar: 2017-12-18 to 2018-01-08
Autumn Exams | bar: 2018-01-15 to 2018-01-22
G53DIA Coursework | bar: 2018-02-12 to 2018-02-19
Easter Holiday
Label | 2018-02-05: 24th April Dissertation Hand In | 17/18th May Presentation and Demo
Week | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14
Documentation
Project Proposal
Revised Project Proposal
Interrim Report
Structure Sections | bar: 2018-03-19
Dissertation | bar: 2018-03-26 to 2018-04-16
Research
Evolutionary Algorithms
Review languages for EAs
Representation
Poké API
Memetic Algorithms | bar: 2018-02-26
Development
Create GA Structure
Run GA on Benchmark Function
Representation
Data import
Validation Method
Basic Methods for GA
Bug Fixing 1
Memetic Algorithms | bar: 2018-03-05 to 2018-03-12
Bug Fixing 2 | bar: 2018-03-12 to 2018-03-19
Demo
Work on Presentation | bar: 2018-04-30 to 2018-05-07
Finalise Presentation | bar: 2018-05-14
Misc
Install software
Run Basic Methods
Running of Final Code | bar: 2018-03-26 to 2018-04-02
Other Commitments
Welcome Week
Christmas Holiday
Autumn Exams
G53DIA Coursework | bar: 2018-03-19 to 2018-03-26
Easter Holiday | bar: 2018-03-26 to 2018-04-16