## Sheet1
Label | Start of Term |  | 13th October Project Proposal |  | 23rd October Revised Project Proposal | [5 empty] | 8th December Interim Report | [19 empty] | 24th April Dissertation Hand In |  | TBA Demo
Week | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30
Documentation
Project Proposal | bar: 2017-10-02 to 2017-10-09
Revised Project Proposal | bar: 2017-10-16
Interrim Report | bar: 2017-11-27 to 2017-12-04
Dissertation | bar: 2018-03-26 to 2018-04-16
Research
Development
Create GA Structure
Misc
Install software
Other Commitments
Welcome Week | bar: 2017-09-25
Christmas Holiday | bar: 2017-12-18 to 2018-01-08
Autumn Exams | bar: 2018-01-15 to 2018-01-22
Easter Holiday | bar: 2018-03-26 to 2018-04-16
GA Structure and libaries happen hand in hand 1 week
Note on A25: Benjamin Joshua Charlton: Not counting in revision time